## Sheet1
| Complete Date | Duration (days)
Development on CIFTP | 2024-04-17 | 16
System Integration Testing Functional | 2024-06-12 | 55
User Acceptance Testing CIFTP Retail | 2024-06-06 | 24
CIFTP Retail Go-Live | 2024-06-14 | 7
User Acceptance Testing Large Value | 2024-07-26 | 41
CIFTP BKLV Go-Live | 2024-08-15 | 19